## Read me
VUB / ULB student housing — decision model
Reference date | 1 October 2026 (year assumed from assignment context)
Status | Screening model; hypothetical acquisition, no selected property
Instructions | Edit blue cells on Inputs. All amounts EUR nominal; unlevered project cash flows.
Decision | Proceed to due diligence only; do not commit to acquisition until permits, costs and rental demand are verified.
Scope | 24 rooms in an existing building near VUB/ULB; acquisition and renovation.
Boundary | Rent excludes recoverable utilities; tenant charges are pass-through and excluded from owner revenue.
Important | Formulas recalculate in Excel/LibreOffice. No property valuation or investment guarantee.
Outputs | Annual cash flow, NPV, IRR, simple payback, affordability and scenario comparison.
Research date | 14 October 2026. Live pages are current evidence, not archived proof of their content on 1 October. Dated 2026–27 and effective-date documents prioritised.
Reproduce | Run python3 enhance_model.py (requires openpyxl). build_model.py saves the basic version first.
Contract duration | Annual occupancy is paid room-months / 12. A 10-month lease without summer letting implies 83.3%, not 95%. See downside.

## Inputs
Input | Value | Unit / interpretation | Evidence status
Rooms | 24 | rooms | Design assumption
Purchase price | 1800000 | EUR | Placeholder; obtain comparable transactions
Acquisition tax | 12.5% | share of purchase price | A1: standard 12.5% Brussels registration duty; no owner-occupier relief assumed
Other acquisition costs | 35000 | EUR excluding acquisition tax | Assumption; notary quote needed
Renovation per room | 30000 | EUR/room incl. nonrecoverable VAT | Assumption; contractor quote needed
Furniture per room | 3500 | EUR/room incl. VAT | Assumption
Contingency | 15% | share of renovation + furniture | Assumption
Initial rent | 550 | EUR/room/month excluding utilities | A2: EUR650 total incl. EUR100 utilities; screening assumption within published ULB EUR500–680 range
Stabilised occupancy | 95% | share of available room months | Assumption
Annual rent growth | 2% | annual nominal escalation | Scenario assumption; indexation legally conditional
Fixed operating cost | 25000 | EUR/year | Insurance, maintenance, admin, property tax allowance
Variable operating cost | 20% | EUR/year: insurance 3000, maintenance 8000, admin 4000, property tax 10000 (all assumptions) | Management, routine repairs, reserve
Operating cost growth | 2.5% | Management 8%, routine repairs 7%, turnover cleaning 5%; excludes capital replacements | Assumption
Discount rate | 6.5% | nominal unlevered required return | Assumption
Exit cap rate | 5.5% | terminal NOI yield | Assumption
Selling costs | 3% | share of terminal value | Assumption
Year 1 occupancy | 75% | ramp-up after renovation at time zero | Assumption
Annual utilities charge | 1200 | EUR/room/year paid by tenant | Assumption; metering needed
Student monthly budget | 1300 | EUR/month available for living | Illustrative; not a statutory living wage
Annual replacement capex | 10000 | EUR/year from year 1 | Separate from routine repairs reserve
Replacement capex growth | 2.5% | annual escalation | Assumption

## Investment
Item | EUR
Purchase | 1800000
Acquisition tax | 225000
Other acquisition costs | 35000
Renovation | 720000
Furniture | 84000
Contingency | 120600
Total initial investment | 2984600

## Cash flow
Year | Rent / room / month | Occupancy | Rent revenue | Fixed costs | Variable costs | NOI | Replacement capex | Terminal proceeds | Project cash flow | Discounted cash flow | Cumulative operating cash flow
0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -2984600 | -2984600 | -2984600
1 | 550 | 0.75 | 118800 | 25000 | 23760 | 70040 | 10000 | 0 | 60040 | 56375.5869 | -2924560
2 | 561 | 0.95 | 153489.6 | 25625 | 30697.92 | 97166.68 | 10250 | 0 | 86916.68 | 76630.8977 | -2837643.32
3 | 572.22 | 0.95 | 156559.392 | 26265.625 | 31311.8784 | 98981.8886 | 10506.25 | 0 | 88475.6386 | 73244.4771 | -2749167.6814
4 | 583.6644 | 0.95 | 159690.5798 | 26922.2656 | 31938.116 | 100830.1982 | 10768.9062 | 0 | 90061.292 | 70006.7219 | -2659106.3894
5 | 595.3377 | 0.95 | 162884.3914 | 27595.3223 | 32576.8783 | 102712.1909 | 11038.1289 | 0 | 91674.062 | 66911.141 | -2567432.3274
6 | 607.2444 | 0.95 | 166142.0793 | 28285.2053 | 33228.4159 | 104628.4581 | 11314.0821 | 0 | 93314.376 | 63951.5256 | -2474117.9515
7 | 619.3893 | 0.95 | 169464.9209 | 28992.3355 | 33892.9842 | 106579.6012 | 11596.9342 | 0 | 94982.667 | 61121.9365 | -2379135.2844
8 | 631.7771 | 0.95 | 172854.2193 | 29717.1438 | 34570.8439 | 108566.2316 | 11886.8575 | 0 | 96679.374 | 58416.693 | -2282455.9104
9 | 644.4127 | 0.95 | 176311.3037 | 30460.0724 | 35262.2607 | 110588.9705 | 12184.029 | 0 | 98404.9415 | 55830.3612 | -2184050.9689
10 | 657.3009 | 0.95 | 179837.5297 | 31221.5742 | 35967.5059 | 112648.4495 | 12488.6297 | 0 | 100159.8198 | 53357.7437 | -2083891.149
11 | 670.4469 | 0.95 | 183434.2803 | 32002.1136 | 36686.8561 | 114745.3107 | 12800.8454 | 0 | 101944.4652 | 50993.8693 | -1981946.6838
12 | 683.8559 | 0.95 | 187102.9659 | 32802.1664 | 37420.5932 | 116880.2063 | 13120.8666 | 0 | 103759.3397 | 48733.9828 | -1878187.3441
13 | 697.533 | 0.95 | 190845.0252 | 33622.2206 | 38169.005 | 119053.7996 | 13448.8882 | 0 | 105604.9113 | 46573.5363 | -1772582.4328
14 | 711.4836 | 0.95 | 194661.9258 | 34462.7761 | 38932.3852 | 121266.7645 | 13785.1104 | 0 | 107481.654 | 44508.1796 | -1665100.7787
15 | 725.7133 | 0.95 | 198555.1643 | 35324.3455 | 39711.0329 | 123519.7859 | 14129.7382 | 0 | 109390.0477 | 42533.752 | -1555710.7311
16 | 740.2276 | 0.95 | 202526.2676 | 36207.4542 | 40505.2535 | 125813.5599 | 14482.9817 | 0 | 111330.5782 | 40646.274 | -1444380.1528
17 | 755.0321 | 0.95 | 206576.7929 | 37112.6405 | 41315.3586 | 128148.7938 | 14845.0562 | 0 | 113303.7376 | 38841.9392 | -1331076.4152
18 | 770.1328 | 0.95 | 210708.3288 | 38040.4565 | 42141.6658 | 130526.2065 | 15216.1826 | 0 | 115310.0239 | 37117.1073 | -1215766.3914
19 | 785.5354 | 0.95 | 214922.4953 | 38991.4679 | 42984.4991 | 132946.5283 | 15596.5872 | 0 | 117349.9411 | 35468.2963 | -1098416.4502
20 | 801.2461 | 0.95 | 219220.9452 | 39966.2546 | 43844.189 | 135410.5016 | 15986.5019 | 2432387.5255 | 2551811.5252 | 724196.5292 | -978992.4505

## Dashboard
Metric | Value | Interpretation
Initial investment | 2984600 | All-in cash outlay at year 0
20-year NPV | -1239139.4491 | Includes resale; positive required for financial acceptance
Project IRR | 2.58% | Unlevered, before income/corporate tax
Year 2 net operating income | 97166.68 | Before replacement capex and financing
Year 2 net cash yield | 2.912% | Annual operating cash / initial investment
Simple operating payback | Not reached in 20 years | Whole-year approximation; excludes resale
Monthly tenant housing cost | 650 | Rent plus utilities
Housing share of student budget | 50% | Illustrative budget; compare affordability
Terminal PV share of benefits | 39.55% | Sensitivity to resale assumptions
Break-even purchase price | 698542.7119 | NPV=0 holding rent, costs and exit yield fixed; negotiation screen
Break-even purchase price | 698542.7119 | NPV=0 holding rent, costs and exit yield fixed; negotiation screen

## Executive report
Executive report — screening recommendation
Proposal | Acquire and renovate an existing 24-room building within walking/cycling distance of VUB/ULB and a frequent tram, metro or rail connection.
Recommendation | Conditional due diligence only. Financial feasibility must be demonstrated after quotes and site checks.
Financial approach | 20-year nominal unlevered DCF with full acquisition costs, renovation, contingency, annual replacement capex and terminal sale.
Environmental | Reuse the existing structure; verify PEB, insulation, heat pumps, ventilation, flood risk, bicycle provision and metered utilities.
Economic | Test rent against furnished student room comparables; tenant utilities shown separately. Contractor and furnishing costs are placeholders.
Social | Balance student affordability, accessible rooms, quiet hours, neighbour engagement and safe routes to campus.
Legal | Confirm planning use, number of units, fire approval, room habitability, lease conditions and municipal requirements before purchase.
Limitations | No identified property; no debt or investor income tax. Cost and rent assumptions require verification.
Base-case results | Investment EUR2,984,600; NPV EUR-1,239,139; IRR 2.58%; operating payback Not reached in 20 years; housing EUR650/month.
Financial decision | Reject acquisition at the assumed price: negative NPV. Renegotiate price, reduce construction costs or seek a transparent subsidy; do not rely on raising rent above affordability limits.
Scenario outcomes | Downside: NPV EUR-2,113,270, IRR -0.52%; Base: NPV EUR-1,239,139, IRR 2.58%; Upside: NPV EUR-608,250, IRR 4.27%
Affordability | EUR650 total is 50% of the illustrative EUR1300 budget. This is a concern despite being within the broad ULB room-cost range. Subsidised university rooms are cheaper.
Preferred search area | Prioritise the Etterbeek station / Petillon / La Plaine corridor for VUB/ULB access. Compare Ixelles cemetery and Solbosch alternatives using address-specific quotes and walking routes. Matrix scores are illustrative.
Investment gates | Positive NPV at the chosen return, validated demand at an affordable rent, confirmed planning/fire/housing compliance, and a funded PEB retrofit. All legal gates remain unverified.
Presentation sequence | 1. Need and location; 2. Assumptions and sources; 3. Costs and cash flow; 4. Scenarios; 5. Environmental/social tradeoffs; 6. Legal gates and conditional decision.
Next 4–8 weeks | Shortlist addresses; obtain planning records and fire advice; commission energy/building surveys; get contractor/notary quotes; collect comparable rents and student budgets. Do not contact sellers or authorities on behalf of the team without separate instruction.
Negotiation screen | Break-even purchase price approximately EUR698,543, holding all other base assumptions fixed.
Base-case results | Investment EUR2,984,600; NPV EUR-1,239,139; IRR 2.58%; operating payback Not reached in 20 years; housing EUR650/month.
Financial decision | Reject acquisition at the assumed price: negative NPV. Renegotiate price, reduce construction costs or seek a transparent subsidy; do not rely on raising rent above affordability limits.
Scenario outcomes | Downside: NPV EUR-2,113,270, IRR -0.52%; Base: NPV EUR-1,239,139, IRR 2.58%; Upside: NPV EUR-608,250, IRR 4.27%
Affordability | EUR650 total is 50% of the illustrative EUR1300 budget. This is a concern despite being within the broad ULB room-cost range. Subsidised university rooms are cheaper.
Preferred search area | Prioritise the Etterbeek station / Petillon / La Plaine corridor for VUB/ULB access. Compare Ixelles cemetery and Solbosch alternatives using address-specific quotes and walking routes. Matrix scores are illustrative.
Investment gates | Positive NPV at the chosen return, validated demand at an affordable rent, confirmed planning/fire/housing compliance, and a funded PEB retrofit. All legal gates remain unverified.
Presentation sequence | 1. Need and location; 2. Assumptions and sources; 3. Costs and cash flow; 4. Scenarios; 5. Environmental/social tradeoffs; 6. Legal gates and conditional decision.
Next 4–8 weeks | Shortlist addresses; obtain planning records and fire advice; commission energy/building surveys; get contractor/notary quotes; collect comparable rents and student budgets. Do not contact sellers or authorities on behalf of the team without separate instruction.
Negotiation screen | Break-even purchase price approximately EUR698,543, holding all other base assumptions fixed.

## Sources
ID | Topic | URL / source | As-of / status | Use in model
A1 | Acquisition duty | https://be.brussels/fr/impots-financement/impots-et-taxes/fiscalite-immobiliere/droits-denregistrement/abattement-sur-les-droits-de-vente | Live official page checked 2026-10-14 | 12.5%; relief conditional, price ceiling EUR600000; no relief modelled
A2 | Market room cost | https://www.ulb.be/fr/partir-ou-venir-en-echange/informations-pour-les-universites-partenaires | Live university guidance checked 2026-10-14 | EUR500–680/month including charges; indicative, not property comparables
A3 | University residence comparator | https://www.ulb.be/medias/fichier/de-brouckere-2026-2027_1772020187753-pdf | Academic year 2026–27 | EUR491 including EUR61 charges; 10-month lease; subsidised university comparator
A4 | Campus transport | https://www.vub.be/nl/over-de-vub/faculteiten-instituten-en-campussen/onze-campussen/vub-main-campus-brussel/bereikbaarheid | Live university page checked 2026-10-14 | Trams 7/25, metro 5 at Petillon, rail at Etterbeek; property walking times unverified
A5 | Housing standards | https://be.brussels/fr/logement/location/conformite-logement/normes-et-securite | Official page; new requirements from 2026-01-01 | Safety, sanitation, equipment; updated standards must be checked room by room
A6 | Student lease | https://be.brussels/nl/huisvesting/huren-en-verhuren/huurovereenkomst/huurcontracten-voor-woningen-modellen-en-bijlage | Live official page checked 2026-10-14 | Student status evidence; maximum 12-month student agreement
A7 | Etterbeek planning | https://etterbeek.brussels/fr/demarches/espace-public-urbanisme/permis-durbanisme-demande | Live municipal page checked 2026-10-14 | Municipal permission and use/unit changes; ask planning department about exact address
A8 | Ixelles planning | https://www.ixelles.be/site/124-Urbanisme | Live municipal page checked 2026-10-14 | PPAS and local planning procedure; check lawful existing use
A9 | Energy requirements | https://environnement.brussels/pro/reglementation-et-inspection/obligations-et-autorisations/objectifs-peb-pour-chaque-bien-et-exigences-peb-en-cas-de-travaux | Live regional environmental authority checked 2026-10-14 | PEB275 by 2033; PEB150 no earlier than 2045; verify unit scope and implementation
A10 | Social integration income | https://primabook.mi-is.be/fr/droit-lintegration-sociale/montants-ris | Effective 2026-09-01 | Monthly cohabitant EUR911.56; single EUR1367.34. Eligibility assessed by CPAS; not automatic student income
A11 | Student quality label | https://be.brussels/fr/logement/location/conformite-logement/label-logement-etudiant | Live regional page checked 2026-10-14 | Quality label supporting housing conformity, student lease and valid PEB
A12 | Lease registration | https://be.brussels/fr/logement/location/bail-dhabitation | Live official page checked 2026-10-14 | Register housing lease within two months; confirm applicable procedure

## Due diligence
Area | Required evidence | Gate / action
Site | Address, floor plans, cadastral records, transit walking time | Select property and verify route on operator timetable
Planning | Authorised use and subdivision; municipal planning advice | Written confirmation before binding purchase
Fire | SIAMU advice, evacuation routes, alarms and compartmentation | Approval and contractor design
Habitation | Surface, daylight, ventilation, sanitation and safety | Assess each room against Brussels Housing Code
Energy | PEB certificate, audit, bills, renovation estimates | Costed retrofit and energy savings
Financial | Three contractor quotes, notary estimate, market comparables | Replace placeholders and rerun scenarios
Social | Student budgets and disability access review | Set affordable room mix and support procedures

## Scenarios
Scenario | Rent multiplier | Occupancy | Renovation multiplier | Exit cap rate | Discount rate | Initial investment | NPV | IRR | Year 2 cash | Interpretation
Downside | 0.9 | 83.33% | 1.2 | 6.5% | 7.5% | 3150200 | -2113270.1526 | -0.5187% | 61065.8 | 10 paid months, rent -10%, renovation +20%, higher yields
Base | 1 | 95% | 1 | 5.5% | 6.5% | 2984600 | -1239139.4491 | 2.58% | 86916.68 | All base assumptions
Upside | 1.1 | 98% | 0.9 | 5% | 6% | 2901800 | -608249.5413 | 4.268% | 103461.2432 | Higher achieved rent and lower renovation cost; unverified

## Scenario cash
Downside cash | Downside PV | Year | Base cash | Base PV | Year | Upside cash | Upside PV | Year
-3150200 | -3150200 | 0 | -2984600 | -2984600 | 0 | -2901800 | -2901800 | 0
50536 | 47010.2326 | 1 | 60040 | 56375.5869 | 1 | 69544 | 65607.5472 | 1
61065.8 | 52842.2282 | 2 | 86916.68 | 76630.8977 | 2 | 103461.2432 | 92080.1381 | 2
62107.741 | 49994.2826 | 3 | 88475.6386 | 73244.4771 | 3 | 105351.0931 | 88454.8092 | 3
63166.0364 | 47298.7616 | 4 | 90061.292 | 70006.7219 | 4 | 107274.2556 | 84971.258 | 4
64240.9013 | 44747.5544 | 5 | 91674.062 | 66911.141 | 5 | 109231.2848 | 81623.9703 | 5
65332.5521 | 42332.9797 | 6 | 93314.376 | 63951.5256 | 6 | 111222.7432 | 78407.6452 | 6
66441.2067 | 40047.763 | 7 | 94982.667 | 61121.9365 | 7 | 113249.2017 | 75317.1872 | 7
67567.0845 | 37885.0152 | 8 | 96679.374 | 58416.693 | 8 | 115311.2394 | 72347.6981 | 8
68710.4062 | 35838.2123 | 9 | 98404.9415 | 55830.3612 | 9 | 117409.4441 | 69494.4696 | 9
69871.3938 | 33901.176 | 10 | 100159.8198 | 53357.7437 | 10 | 119544.4125 | 66752.9756 | 10
71050.2706 | 32068.0557 | 11 | 101944.4652 | 50993.8693 | 11 | 121716.7497 | 64118.8654 | 11
72247.2612 | 30333.311 | 12 | 103759.3397 | 48733.9828 | 12 | 123927.0699 | 61587.9571 | 12
73462.5913 | 28691.6952 | 13 | 105604.9113 | 46573.5363 | 13 | 126175.9962 | 59156.2307 | 13
74696.4876 | 27138.2401 | 14 | 107481.654 | 44508.1796 | 14 | 128464.1606 | 56819.8221 | 14
75949.1779 | 25668.2413 | 15 | 109390.0477 | 42533.752 | 15 | 130792.2043 | 54575.0171 | 15
77220.891 | 24277.2439 | 16 | 111330.5782 | 40646.274 | 16 | 133160.778 | 52418.2454 | 16
78511.8567 | 22961.0295 | 17 | 113303.7376 | 38841.9392 | 17 | 135570.5414 | 50346.0753 | 17
79822.3053 | 21715.6038 | 18 | 115310.0239 | 37117.1073 | 18 | 138022.1637 | 48355.2081 | 18
81152.4682 | 20537.1849 | 19 | 117349.9411 | 35468.2963 | 19 | 140516.3238 | 46442.4732 | 19
1578675.7869 | 371641.0368 | 20 | 2551811.5252 | 724196.5292 | 20 | 3286264.6956 | 1024672.8659 | 20

## Environment
Metric | Before | After | Unit / evidence
Floor area | 600 | 600 | m2; design assumption
Delivered energy intensity | 250 | 120 | kWh/m2/year; assumptions, distinct from regulatory PEB primary-energy rating
Energy price | 0.15 | 0.15 | EUR/kWh; assumption not a supplier quote
Operational emissions factor | 0.2 | 0.2 | kgCO2e/kWh; illustrative, replace with heating-system factors
Annual energy use | 150000 | 72000 | kWh/year
Annual utility expense | 22500 | 10800 | EUR/year; tenant benefit, excluded from owner DCF
Annual operational emissions | 30 | 14.4 | tonnesCO2e/year; embodied carbon excluded
Annual energy saved |  | 78000 | kWh/year
Annual emissions avoided |  | 15.6 | tonnesCO2e/year
Retrofit measures | Insulation, airtightness, shading, ventilation | Metering, efficient heating, water saving | Cost included in renovation budget; audit needed
Regulatory target A9 | PEB275 by 2033 | PEB150 no earlier than 2045 | Check current implementing rules; aim for C where technically feasible

## Social and services
Measure | Value | Meaning / action
Total monthly housing | 650 | Rent plus utilities
Illustrative student budget | 1300 | Assumption; survey target students
Housing budget share | 50% | Above 40% is a project screening concern, not a legal threshold
Single-person RIS | 1367.34 | A10 effective September 2026; eligibility is individual CPAS decision
Cohabitant RIS | 911.56 | A10 effective September 2026; shared housing status needs CPAS assessment
Share of single RIS | 47.54% | Affordability stress indicator
Share of cohabitant RIS | 71.31% | Affordability stress indicator
Included in rent | Furniture, Wi-Fi, communal cleaning | Supplier quotes; operator costs in owner budget
Utilities | EUR100/month provisional | Annual reconciliation, clear allocation and separate bills
Optional services | Laundry paid at cost; no meal plan | No additional profit assumed
Neighbourhood | Quiet hours, complaint contact, waste separation | Pre-opening neighbour meeting; monitor complaints
Inclusion | Accessible ground-floor room and step-free route | Architect to verify feasibility and cost
Support | University social services / CPAS referral | Do not assume grants as recurring owner income

## Decision matrix
Criterion | Weight | Etterbeek-Petillon | Ixelles cemetery | Solbosch edge | Basis / illustrative scores 1–5
Transport | 0.25 | 5 | 4 | 4 | A4; test actual walking route and service frequency
Campus access | 0.2 | 5 | 5 | 5 | VUB/ULB proximity; exact address needed
Affordability | 0.2 | 3 | 3 | 3 | Same base budget; acquisition prices unverified
Environmental potential | 0.15 | 3 | 3 | 3 | No audited building; neutral scores
Social fit | 0.1 | 3 | 3 | 4 | Judgement only; survey neighbours
Execution risk | 0.1 | 3 | 3 | 3 | No site-specific permission assessed
Weight total | 1
Weighted score |  | 3.9 | 3.65 | 3.75 | Scores are provisional; no property ranking established
Legal gate | UNKNOWN | UNKNOWN | UNKNOWN | UNKNOWN | Any failure overrides score and NPV; no acquisition authorised

## Legal and risks
Issue | Rule / evidence | Status | Next action | Owner
Registration duty | 12.5% on existing-building purchase A1 | Modelled | Notary confirms tax base and VAT status | Notary
Planning | Municipal permits; lawful use and unit count A7/A8 | UNVERIFIED | Obtain planning records; sale condition precedent | Architect
Habitability | Brussels minimum standards changed January 2026 A5 | UNVERIFIED | Room-by-room compliance survey | Architect
Fire | Smoke detection and fire safety A5 | UNVERIFIED | Consult SIAMU; cost evacuation and compartmentation | Fire engineer
Lease | Student evidence and max 12 months A6; register within two months A12 | UNVERIFIED | Use current regional template; review deposit and termination | Legal adviser
Rent | Indexation and rent fairness subject to regional rules | UNVERIFIED | Check reference rent and current indexation restrictions | Legal adviser
Energy | Regional PEB targets A9; certificate A11 | UNVERIFIED | Obtain certificate, audit and staged retrofit plan | Energy auditor
Tax | Investor income tax and VAT depend on entity and services | EXCLUDED | Add entity-specific taxation before investment decision | Accountant
Overruns | 15% contingency, downside +20% renovation | Scenario | Fixed scope and quotes; inspect structural condition | Project manager
Letting | 95% paid occupancy assumes summer demand | Scenario | Validate academic vs full-year lease mix | Operator
Municipal charges | Property tax, local taxes and permit fees vary by address | ALLOWANCE | Replace EUR10000 tax allowance with actual assessment | Accountant